## Sheet1
Tier | Project | Index | Type | Description
1 | portal | 1 | process | Requirements
1 | portal | 2 | process | Planning
1 | portal | 3 | process | Design
1 | portal | 4 | process | Implementation
1 | portal | 5 | process | Content Integration
1 | portal | 6 | process | Deployment
1 | portal | 7 | process | Future Enhancements

## WBS Task List
Work Breakdown Structure
Start Date: | 2025-02-10 |  |  |  |  | Current Date: | 2025-03-01
Level 1 | Level 2 | Level 3 | ID | Start Date | Completetion | Task | Task Description | estimate | Predecessor | Completion | Column2
1 - Project | Header | Header | 1 | 2025-02-10 | 2025-02-14 | Complete Project | Project | 4 |  | 0% | 0
2 - Process | 1 - Requirement | Header | 1.1 | 2025-02-10 | 2025-02-10 | Complete Requirements | Requirements | 0 |  |  | 0
3 - Package | 1 - Requirement | 1 - Work Order | 1.1.1 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.1 | Deliverable: Mainenance Request System | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 1 - Requirement | 2 - Accounting & Analytics | 1.1.2 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.2 | Deliverable: Accounting and Analytical Tools | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 1 - Requirement | 3 - Training Materials | 1.1.3 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.3 | Deliverable: User Guides, training materials, tutorials | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
2 - Process | 2 - Planning | Header | 1.2 | 2025-02-11 | 2025-02-11 | Complete Planning Phase | Planning Phase | 0 | 1.1 |  | 0
3 - Package | 2 - Planning | 1 - Work Order | 1.2.1 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.1 | Deliverable: Mainenance Request System | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 2 - Planning | 2 - Accounting & Analytics | 1.2.2 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.2 | Deliverable: Accounting and Analytical Tools | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 2 - Planning | 3 - Training Materials | 1.2.3 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.3 | Deliverable: User Guides, training materials, tutorials | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
2 - Process | 3 - Design | Header | 1.3 | 2025-02-12 | 2025-02-12 | Complete Design Phase | Design Phase | 0 | 1.2 |  | 0
3 - Package | 3 - Design | 1 - Work Order | 1.3.1 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.1 | Deliverable: Mainenance Request System | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 3 - Design | 2 - Accounting & Analytics | 1.3.2 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.2 | Deliverable: Accounting and Analytical Tools | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 3 - Design | 3 - Training Materials | 1.3.3 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.3 | Deliverable: User Guides, training materials, tutorials | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
2 - Process | 4 - Implementation | Header | 1.4 | 2025-02-13 | 2025-02-13 | Complete Implmentation Phase | Implementation Phase | 0 | 1.3 |  | 0
3 - Package | 4 - Implementation | 1 - Work Order | 1.4.1 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.1 | Deliverable: Mainenance Request System | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 4 - Implementation | 2 - Accounting & Analytics | 1.4.2 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.2 | Deliverable: Accounting and Analytical Tools | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 4 - Implementation | 3 - Training Materials | 1.4.3 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.3 | Deliverable: User Guides, training materials, tutorials | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
2 - Process | 5 - Deployment | Header | 1.5 | 2025-02-14 | 2025-02-14 | Completion Deployment Phase | Deployment Phase | 0 | 1.4 |  | 0
3 - Package | 5 - Deployment | 1 - Work Order | 1.5.1 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.1 | Deliverable: Mainenance Request System | 0 |  |  | 0
4 - task |  |  | 1.5.1.1 |  | Dec 21 | Integrate supporting documents: Yahtzee - Project Charter and System Overview | Upload portal supporting document Project Charter & Systems Overview |  |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 5 - Deployment | 2 - Accounting & Analytics | 1.5.2 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.2 | Deliverable: Accounting and Analytical Tools | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
3 - Package | 5 - Deployment | 3 - Training Materials | 1.5.3 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.3 | Deliverable: User Guides, training materials, tutorials | 0 |  |  | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
4 - task | [10 empty] | 0
Formulas:
Start Date = [Start Date, row above]
Completetion = MAX([Completetion, row below],G25,G38,G51,G64)
Completetion = MAX([Completetion, row below]:G24)
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Please use the filters below to select which sections of the project you want to see

## Gantt Chart for WBS
|  |  | Final Project: Gantt Chart |  |  |  |  | Use the slicers below to filter which parts of the project you want to see | End Date: | 2025-02-19
DO NOT ALTER CELL BELOW
45707
Property Management App Tasks
Level 1 | Level 2 | Level 3 | Task ID | START DATE | END DATE | DESCRIPTION | DURATION (Days)
1 - Project | Header | Header | 1 | 2025-02-10 | 2025-02-14 | Complete Project | 4
2 - Process | 1 - Requirement | Header | 1.1 | 2025-02-10 | 2025-02-10 | Complete Requirements | 0
3 - Package | 1 - Requirement | 1 - Work Order | 1.1.1 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.1 | 0
4 - task | 1 - Requirement | 1 - Work Order | 1.1.1.1 | missing |  | missing | missing
4 - task | 1 - Requirement | 1 - Work Order | 1.1.1.2 | missing |  | missing | missing
4 - task | 1 - Requirement | 1 - Work Order | 1.1.1.3 | missing |  | missing | missing
3 - Package | 1 - Requirement | 2 - Accounting & Analytics | 1.1.2 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.2 | 0
4 - task | 1 - Requirement | 2 - Accounting & Analytics | 1.1.2.1 | missing |  | missing | missing
4 - task | 1 - Requirement | 2 - Accounting & Analytics | 1.1.2.2 | missing |  | missing | missing
4 - task | 1 - Requirement | 2 - Accounting & Analytics | 1.1.2.3 | missing |  | missing | missing
3 - Package | 1 - Requirement | 3 - Training Materials | 1.1.3 | 2025-02-10 | 2025-02-10 | Complete Requirements: Package 1.1.3 | 0
4 - task | 1 - Requirement | 3 - Training Materials | 1.1.3.1 | missing |  | missing | missing
4 - task | 1 - Requirement | 3 - Training Materials | 1.1.3.2 | missing |  | missing | missing
4 - task | 1 - Requirement | 3 - Training Materials | 1.1.3.3 | missing |  | missing | missing
2 - Process | 2 - Planning | Header | 1.2 | 2025-02-11 | 2025-02-11 | Complete Planning Phase | 0
3 - Package | 2 - Planning | 1 - Work Order | 1.2.1 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.1 | 0
4 - task | 2 - Planning | 1 - Work Order | 1.2.1.1 | missing |  | missing | missing
4 - task | 2 - Planning | 1 - Work Order | 1.2.1.2 | missing |  | missing | missing
4 - task | 2 - Planning | 1 - Work Order | 1.2.1.3 | missing |  | missing | missing
3 - Package | 2 - Planning | 2 - Accounting & Analytics | 1.2.2 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.2 | 0
4 - task | 2 - Planning | 2 - Accounting & Analytics | 1.2.2.1 | missing |  | missing | missing
4 - task | 2 - Planning | 2 - Accounting & Analytics | 1.2.2.2 | missing |  | missing | missing
4 - task | 2 - Planning | 2 - Accounting & Analytics | 1.2.2.3 | missing |  | missing | missing
3 - Package | 2 - Planning | 3 - Training Materials | 1.2.3 | 2025-02-11 | 2025-02-11 | Complete Planning: Package 1.2.3 | 0
4 - task | 2 - Planning | 3 - Training Materials | 1.2.3.1 | missing |  | missing | missing
4 - task | 2 - Planning | 3 - Training Materials | 1.2.3.2 | missing |  | missing | missing
4 - task | 2 - Planning | 3 - Training Materials | 1.2.3.3 | missing |  | missing | missing
2 - Process | 3 - Design | Header | 1.3 | 2025-02-12 | 2025-02-12 | Complete Design Phase | 0
3 - Package | 3 - Design | 1 - Work Order | 1.3.1 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.1 | 0
4 - task | 3 - Design | 1 - Work Order | 1.3.1.1 | missing |  | missing | missing
4 - task | 3 - Design | 1 - Work Order | 1.3.1.2 | missing |  | missing | missing
3 - Package | 3 - Design | 2 - Accounting & Analytics | 1.3.2 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.2 | 0
4 - task | 3 - Design | 2 - Accounting & Analytics | 1.3.2.1 | missing |  | missing | missing
4 - task | 3 - Design | 2 - Accounting & Analytics | 1.3.2.2 | missing |  | missing | missing
3 - Package | 3 - Design | 3 - Training Materials | 1.3.3 | 2025-02-12 | 2025-02-12 | Complete Design: Package 1.3.3 | 0
4 - task | 3 - Design | 3 - Training Materials | 1.3.3.1 | missing |  | missing | missing
2 - Process | 4 - Implementation | Header | 1.4 | 2025-02-13 | 2025-02-13 | Complete Implmentation Phase | 0
3 - Package | 4 - Implementation | 1 - Work Order | 1.4.1 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.1 | 0
4 - task | 4 - Implementation | 1 - Work Order | 1.4.1.1 | missing |  | missing | missing
4 - task | 4 - Implementation | 1 - Work Order | 1.4.1.2 | missing |  | missing | missing
4 - task | 4 - Implementation | 1 - Work Order | 1.4.1.3 | missing |  | missing | missing
3 - Package | 4 - Implementation | 2 - Accounting & Analytics | 1.4.2 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.2 | 0
4 - task | 4 - Implementation | 2 - Accounting & Analytics | 1.4.2.1 | missing |  | missing | missing
4 - task | 4 - Implementation | 2 - Accounting & Analytics | 1.4.2.2 | missing |  | missing | missing
4 - task | 4 - Implementation | 2 - Accounting & Analytics | 1.4.2.3 | missing |  | missing | missing
3 - Package | 4 - Implementation | 3 - Training Materials | 1.4.3 | 2025-02-13 | 2025-02-13 | Complete Implementation: Package 1.4.3 | 0
4 - task | 4 - Implementation | 3 - Training Materials | 1.4.3.1 | missing |  | missing | missing
4 - task | 4 - Implementation | 3 - Training Materials | 1.4.3.2 | missing |  | missing | missing
4 - task | 4 - Implementation | 3 - Training Materials | 1.4.3.3 | missing |  | missing | missing
2 - Process | 5 - Deployment | Header | 1.5 | 2025-02-14 | 2025-02-14 | Completion Deployment Phase | 0
3 - Package | 5 - Deployment | 1 - Work Order | 1.5.1 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.1 | 0
4 - task | 5 - Deployment | 1 - Work Order | 1.5.2.1 | missing |  | missing | missing
4 - task | 5 - Deployment | 1 - Work Order | 1.5.2.2 | missing |  | missing | missing
3 - Package | 5 - Deployment | 2 - Accounting & Analytics | 1.5.2 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.2 | 0
4 - task | 5 - Deployment | 2 - Accounting & Analytics | 1.5.2.1 | missing |  | missing | missing
4 - task | 5 - Deployment | 2 - Accounting & Analytics | 1.5.2.2 | missing |  | missing | missing
3 - Package | 5 - Deployment | 3 - Training Materials | 1.5.3 | 2025-02-14 | 2025-02-14 | Complete Deployment: Package 1.5.3 | 0
4 - task | 5 - Deployment | 3 - Training Materials | 1.5.3.1 | missing |  | missing | missing
4 - task | 5 - Deployment | 3 - Training Materials | 1.5.3.2 | missing |  | missing | missing
Formulas:
START DATE = XLOOKUP([Task ID],wbs[ID],wbs[Start Date],"missing",0)
END DATE = XLOOKUP([Task ID],wbs[ID],wbs[Completetion],"",0)
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Sheet2
Portal Scope: Packages
Project | Level | Package No. | Package ID | Package Name | Sub-Package 1 | Package Type | sub-package description
Portal | Project |  |  | Portal: Portfolio Section | Hospital Triage App | Main
Portal | Project |  |  | Portal: Portfolio Section | Hospital Triage App | Support Document | Project Charter and Systems Overview
Portal | Project |  |  | Portal: Portfolio Section | Hospital Triage App | Support Document | Database Overview
Portal | Project |  |  | Portal: Portfolio Section | Yahtzee Game
Portal | Project |  |  | Portal: Portfolio Section | Dashboard App
Portal | Project |  |  | Portal: Portfolio Section | Shift Tracker
Portal | Project |  |  | Portal: Portfolio Section | Budget Tracker
Portal | Project |  |  | Portal: Portfolio Section | Schedule Tracker

## Sheet3
Documentation
ID | Level | Level Type | Name | Descriptoin
PORT | Project | - | Portal
YAHT | Project | - | Yahtzee Game
TRIG | Project | - | Triage App
DASH-01 | Project | - | Dashboard App
SHFT | Project | - | Shift Tracker
BUDG | Project | - | Budget Tracker
SCHE | Project | - | Schedule Tracker
REQ
PKG